PlushPal

MVP Detailed
Implementation Plan

Execution roadmap for iPhone, Android, macOS, and Windows

Version:  1.1

Status:  Execution baseline

Date:  June 18, 2026

Target:  Supervised cross-platform private beta

Companion:  Product Requirements and Architecture Specification v5.0

Delivery decision

Eight gate-driven two-week sprints: feasibility, foundation, desktop vertical slice, local product, iOS, Android, connected features, and hardening.

# Contents

1 Purpose and delivery outcome

2 Scope

3 Architecture baseline

4 Team and planning assumptions

5 Delivery roadmap

6-13 Sprint execution plan

14 Cross-cutting workstreams

15 Test architecture

16 First sprint-ready backlog

17 First ten working days

18 Definitions of ready and done

19 Decision ownership

20 Risks and contingencies

21 Path to public release

22 Immediate start checklist

Appendices A-D

# 1. Purpose and delivery outcome

This plan turns the approved PlushPal architecture into an executable delivery program. The first target is a supervised private beta that runs end to end on macOS, Windows, iPhone, and Android: parent onboarding, device assessment, local model installation, character and voice enrollment, local speech-to-text, age-controlled local conversation, optional experimental cloud conversation, local safety validation, local voice synthesis, encrypted storage, and complete local deletion.

The private beta is not a public child-directed store release. Public release requires separate provider contracts, child-privacy review, safety validation, store declarations, and release gates described in this plan.

## 1.1 MVP completion statement

The MVP is complete when a parent can configure one child age band and at least one character; a child can complete a stable ten-turn push-to-talk conversation with a capability-approved local model; all raw audio and voice assets remain local; conversation history follows the selected local retention policy; optional search and experimental cloud paths transmit only allowlisted text; and the complete workflow passes privacy, safety, interruption, recovery, and deletion tests on the supported device matrix.

## 1.2 Delivery principles

Build one walking skeleton before broad feature work.

Keep orchestration, policies, provider routing, and repositories in the shared Rust core.

Keep platform SDK details in thin Swift, Kotlin, and desktop adapters.

Keep C++ limited to speech and local-model inference boundaries.

Make local mode the default and cloud mode an explicit parent choice.

Treat safety, privacy, and deletion as product features with automated tests.

Use release gates instead of calendar pressure to approve higher-risk stages.

# 2. Scope

## 2.1 In-scope MVP capabilities

Shared Flutter interface for parent and child workflows.

Parent PIN and platform authentication where available.

Age-band policy selection for 4-5, 6-8, and 9-12.

Device capability benchmark and signed model recommendation manifest.

Downloadable Qwen3 1.7B Q4 baseline and Qwen3 4B Q4 capable-device tier, subject to benchmark approval.

Local STT using the selected Sherpa-ONNX-compatible model.

Local conversation inference through llama.cpp.

Local zero-shot or reference-conditioned TTS through the selected ZipVoice-compatible deployment, subject to feasibility gate.

Character creation, voice enrollment, preview, enable/disable, and deletion.

Session-only history by default; optional encrypted local persistence.

Local input screening, immutable age policy, structured output, local output screening, and safe fallbacks.

Curated web lookup proof of concept for approved factual domains.

Experimental OpenAI-compatible BYOK adapter for supervised development testing only.

Signed desktop host serving embedded Flutter web assets over protected loopback.

Native iOS and Android application hosts.

Local redacted diagnostics and delete-all.

## 2.2 Explicitly deferred

Public child-directed App Store and Play Store launch.

PlushPal accounts, synchronization, hosted conversation gateway, subscriptions, and billing.

Unrestricted web browsing and open-ended agents.

Wake words, continuous listening, background capture, and smart-toy hardware connectivity.

Multiple children, shared family accounts, remote parent dashboards, and cross-device history.

Public voice export, voice sharing, character marketplace, and community content.

Languages other than English.

Guaranteed local LLM operation on every device.

Automatic cloud analytics or crash-report uploads.

# 3. Architecture baseline

| Layer | MVP implementation | Responsibility |
| --- | --- | --- |
| Presentation | Flutter | Parent/child screens, accessibility, state rendering, local desktop web build |
| Application core | Rust | Use cases, session state, age policy, prompt compiler, repositories, provider routing, typed events |
| Local LLM | llama.cpp through C ABI | GGUF model loading, generation, cancellation, token accounting |
| Speech | C++/Sherpa-ONNX adapters | STT, audio normalization, speaker preparation, TTS |
| Mobile hosts | Swift and Kotlin | Permissions, audio sessions, lifecycle, Keychain/Keystore, native networking |
| Desktop host | Rust executable | Loopback gateway, embedded web assets, credential vault, database, native audio/inference |
| Storage | SQLCipher plus encrypted files | Profiles, settings, optional transcripts, voice assets, model manifests |
| Cloud adapter | Rust/native HTTPS | Experimental stateless text-only provider calls |
| Curated search | Rust/native HTTPS | Sanitized queries, bounded evidence, untrusted-content handling |

## 3.1 Dependency rule

Flutter SHALL never access SQL, model files, provider keys, or voice assets directly. The shared core SHALL depend on interfaces for storage, inference, networking, key management, and clocks. Platform adapters SHALL implement those interfaces. Local providers receive bounded internal context; cloud and search adapters receive separate allowlisted DTOs and SHALL not query repositories directly.

## 3.2 Runtime sequence

Flutter command
  -> platform bridge
  -> Rust use case
  -> audio/STT adapter
  -> local input policy
  -> local or experimental cloud conversation provider
  -> structured response validator
  -> local output policy
  -> local TTS
  -> typed progress/playback events
  -> Flutter state

# 4. Team and planning assumptions

The baseline plan assumes the following effective capacity:

| Role | Allocation | Primary ownership |
| --- | --- | --- |
| Technical lead / principal engineer | 1.0 | Architecture, interfaces, reviews, release gates |
| Rust and inference engineer | 1.0 | Core, llama.cpp, speech ABI, desktop host |
| Flutter/mobile engineer A | 1.0 | Shared UI, iOS host, accessibility |
| Flutter/mobile engineer B | 1.0 | Shared UI, Android host, model manager |
| QA/automation engineer | 1.0 | Device automation, privacy tests, regression suites |
| Product designer/researcher | 0.5 | Parent onboarding, child interaction, usability |
| Safety/privacy advisor | 0.25 | Policy corpus, disclosures, retention and provider review |

With fewer than four full-time engineers, preserve the milestone order and reduce simultaneous platform work rather than weakening architecture, safety, or test scope. All estimates are planning ranges, not commitments, and shall be recalibrated after the feasibility gate.

# 5. Delivery roadmap

The plan uses eight two-week sprints for the private-beta target. The calendar may change after model benchmarks; exit criteria do not.

| Sprint | Goal | Demonstrable outcome | Exit gate |
| --- | --- | --- | --- |
| 0 | Feasibility and decisions | Benchmarked STT, local LLM, TTS, and ABI prototypes | G0 feasibility |
| 1 | Repository and core foundation | CI, core state machine, generated interfaces, encrypted test repository | G1 foundation |
| 2 | Desktop walking skeleton | Record -> STT -> local LLM -> standard TTS -> playback | G2 vertical slice |
| 3 | Voice, policy, and model management | Voice enrollment, cloned preview, age policies, model installer | G3 local MVP |
| 4 | iOS integration | Complete supervised workflow on reference iPhones | G4 iOS |
| 5 | Android integration | Complete supervised workflow on reference Android devices | G5 Android |
| 6 | Cloud experiment and curated search | Stateless BYOK testing, local history, bounded web evidence | G6 feature complete |
| 7 | Hardening and private beta | Security, privacy, safety, accessibility, recovery, installers | G7 private beta |

Public store release begins only after G7 and adds provider contracting, independent review, store compliance, and expanded beta evidence.

# 6. Sprint 0: feasibility and architecture decisions

## 6.1 Objectives

Prove the three highest-risk capabilities before building product surfaces: child-speech STT, useful local conversation, and acceptable voice-cloning TTS on representative hardware. Prove that Rust, C++, Flutter, iOS, Android, and desktop can exchange asynchronous jobs safely.

## 6.2 Work items

SPIKE-INF-001: Device matrix. Acquire or nominate at least two iPhones, two Android phones, one Apple Silicon Mac, and one Windows x64 computer. Record OS, memory class, storage, CPU/GPU/NPU, and thermal behavior.

SPIKE-INF-002: Local LLM benchmark. Convert or obtain verified GGUF Q4 builds of candidate 1.7B and 4B models. Measure download size, load time, first-token latency, tokens per second, peak memory, 10-turn stability, and output quality in short child-dialogue prompts.

SPIKE-STT-001: STT benchmark. Evaluate at least one compact English STT model using child and adult test recordings across quiet, normal-home, and moderate-noise conditions. Measure word error rate, end-of-speech latency, memory, and recovery after interruption.

SPIKE-TTS-001: Voice-cloning benchmark. Validate the selected zero-shot TTS engine with 15-, 20-, and 30-second authorized reference samples. Measure speaker similarity, intelligibility, synthesis real-time factor, peak memory, and failure behavior.

SPIKE-ABI-001: Native boundary. Build a minimal Rust host calling a C ABI for a cancellable inference job and emitting progress events. Verify AddressSanitizer and thread-safety behavior on desktop.

SPIKE-MOB-001: Flutter/native bridge. Prove one asynchronous native job, cancellation, progress, and buffer transfer on iOS and Android without blocking the UI thread.

SPIKE-LIC-001: License inventory. Record source, model license, redistribution rights, commercial-use restrictions, attribution, checksum, and version for every candidate runtime and weight file.

## 6.3 Deliverables

Benchmark report and raw result schema.

Approved model shortlist and minimum-device proposal.

C ABI v0 prototype.

ADR-001 through ADR-006 covering shared core, UI, speech runtime, local LLM runtime, storage, and desktop delivery.

Updated risk register and estimates.

## 6.4 G0 acceptance criteria

At least one STT configuration meets the provisional accuracy and latency targets on minimum devices.

At least one local model produces coherent three-sentence dialogue at acceptable latency on a standard phone.

Voice cloning works acceptably on desktop and at least one target phone, or a documented fallback plan is approved.

No unresolved license blocker exists for the selected private-beta distribution.

The native job prototype cancels cleanly and passes memory-safety instrumentation.

If TTS cannot meet mobile targets, the MVP SHALL use a standard local TTS voice on mobile while retaining cloned voice on desktop until a replacement model passes. The architecture must not be rewritten around one TTS engine.

# 7. Sprint 1: foundation

## 7.1 Repository bootstrap

Create the monorepo:

plushpal/
  apps/flutter_ui/
  apps/ios_host/
  apps/android_host/
  apps/desktop_host/
  crates/core_domain/
  crates/application/
  crates/policy_engine/
  crates/provider_api/
  crates/local_llm_llamacpp/
  crates/search_api/
  crates/curated_search/
  crates/encrypted_storage/
  crates/desktop_gateway/
  native/inference_abi/
  native/speech_engine/
  schemas/events/
  schemas/local_api/
  schemas/search_evidence/
  models/manifests/
  tests/privacy/
  tests/safety/
  tests/e2e/
  docs/adr/

## 7.2 Work items

FOUND-REP-001: Pin Flutter, Dart, Rust, CMake, compilers, ONNX Runtime, llama.cpp, and code-generation versions. Add reproducible bootstrap scripts.

FOUND-CI-001: Add formatting, linting, unit tests, desktop debug builds, dependency/license scanning, secret scanning, and artifact retention. Mobile simulator builds become required before Sprint 4.

FOUND-SCHEMA-001: Define versioned command, event, provider-response, error, and model-manifest schemas. Generate Dart/Rust/native bindings where practical.

FOUND-ELIG-001: Define a signed, expiring provider-eligibility registry keyed by provider, model, region, age range, retention requirement, and release channel. The runtime fails closed when eligibility is missing, expired, or incompatible.

CORE-STATE-001: Implement the conversation state machine: Idle, Capturing, Transcribing, ScreeningInput, Generating, ScreeningOutput, Synthesizing, Playing, Cancelled, and Failed.

CORE-JOB-001: Implement job IDs, deadlines, cancellation tokens, typed progress events, stale-result rejection, and one-active-turn-per-session behavior.

CORE-ERR-001: Define normalized errors for permission, model, storage, provider, policy, timeout, resource pressure, cancellation, and internal failures.

STORE-001: Implement encrypted repository interfaces, schema migrations, transactional writes, and in-memory test adapters.

KEY-001: Define the secret-reference and wrapped-key interfaces. Add desktop development implementation without storing real secrets in source or fixtures.

## 7.3 G1 acceptance criteria

A fresh checkout can build and test through documented commands.

CI rejects formatting, lint, test, secret, and license failures.

The core state machine has exhaustive transition tests.

Cancellation and stale response tests pass under randomized timing.

Database migration v1 and encrypted repository round-trip tests pass.

# 8. Sprint 2: desktop walking skeleton

## 8.1 Desktop host

DSK-HOST-001: Build the Rust desktop executable that serves embedded Flutter web assets, binds only to loopback, selects an ephemeral port, creates a launch secret, and opens the default browser.

DSK-SEC-001: Implement Host and Origin validation, strict CORS, restrictive CSP, authenticated WebSocket upgrade, payload caps, idle shutdown, and DNS-rebinding tests.

DSK-AUD-001: Implement microphone selection, capture, VAD boundary, playback, cancellation, and audio-route error handling.

## 8.2 Walking-skeleton conversation

INF-STT-001: Wrap the approved STT engine behind SpeechToText with model load, utterance transcription, progress, confidence where supported, and cancellation.

INF-LLM-001: Wrap llama.cpp behind ConversationProvider, including model load, token streaming to the core, sampling configuration, context cap, deadline, and cancellation.

INF-TTS-001: Use standard local TTS temporarily if cloned TTS is not ready. Return typed PCM/audio frames through the playback adapter.

UI-CONV-001: Implement a developer conversation screen showing selected character, state, push-to-talk, cancel, progress, non-sensitive errors, and playback.

E2E-DSK-001: Automate the deterministic path using fixture audio and a deterministic model/provider test double; maintain a manual physical-audio test checklist.

## 8.3 G2 acceptance criteria

Signed-development desktop host starts without Node or npm.

Browser UI cannot access the service without the launch session.

Fixture and live microphone audio complete STT -> LLM -> TTS -> playback.

A turn can be cancelled during every asynchronous stage.

Ten sequential turns complete without stale playback, resource leakage, or corrupted state.

# 9. Sprint 3: local product MVP

## 9.1 Parent onboarding

UI-ONB-001: Build disclosure, parent PIN, age-band, device assessment, model recommendation, download acknowledgement, and completion screens.

POL-AGE-001: Implement immutable versioned age policies for 4-5, 6-8, and 9-12. Policies control sentence/character limits, vocabulary guidance, search access, prohibited behavior, personal-data handling, and trusted-adult escalation.

MODEL-MGR-001: Implement signed manifest retrieval, local bundled fallback manifest, free-space check, resumable download where supported, checksum/signature verification, staging, atomic activation, rollback, and uninstall.

MODEL-BENCH-001: Run a bounded local benchmark and recommend lite, standard, enhanced, or unsupported. Persist only capability classification and non-sensitive benchmark results.

## 9.2 Character and voice

CHR-001: Implement character create/edit/enable/disable/delete with approved personality vocabulary and parent guidance limits.

VOICE-001: Implement WAV/common-audio import, local transcode, duration/noise/clipping validation, authorization attestation, local speaker preparation, encrypted storage, and preview.

VOICE-DEL-001: Implement character crypto-erasure, cache cleanup, database cascade, interrupted-deletion recovery, and verification tests.

## 9.3 Safety pipeline

SAFE-IN-001: Implement local PII patterns, unsupported-language detection, high-confidence block/escalation categories, and input length limits.

SAFE-PROMPT-001: Implement versioned system instructions, age policy, character fields, untrusted transcript delimiters, bounded context, and structured response schema.

SAFE-OUT-001: Implement strict JSON parsing, sentence/character limits, URL/contact detection, prohibited request patterns, markup stripping, and safe local fallbacks.

SAFE-CORPUS-001: Create the initial automated corpus for prompt injection, secrecy, contact exchange, dangerous activity, sexual content, graphic violence, manipulation, distress, abuse disclosure, benign near-matches, and age appropriateness.

## 9.4 G3 acceptance criteria

A parent can complete onboarding and install a recommended model.

A parent can enroll and delete a voice without network transmission.

Local conversations apply the selected age policy and produce valid structured responses.

Every failed policy stage results in an approved local fallback and no TTS of rejected content.

Delete-character and delete-all pass after normal, cancelled, and crash-recovery scenarios.

# 10. Sprint 4: iOS integration

## 10.1 Work items

IOS-BRIDGE-001: Package Rust and C++ artifacts for device and simulator development, expose the versioned ABI, and implement generated Flutter plugin calls.

IOS-KEY-001: Implement Keychain-wrapped installation keys and secret references. Verify that API keys never return to Dart.

IOS-STORE-001: Configure application support directories, file-protection classes, backup exclusions, SQLCipher, model storage, and migration recovery.

IOS-AUD-001: Implement AVAudioSession and AVAudioEngine capture/playback, permission timing, interruption, route changes, Bluetooth policy, calls, headphones, device lock, and cancellation.

IOS-MEM-001: Implement memory-pressure events and model eviction. Benchmark sequential and resident STT/LLM/TTS strategies.

IOS-UI-001: Complete parent and child flows, dynamic text, VoiceOver labels, focus order, reduced motion, and touch targets.

IOS-E2E-001: Run automated state tests and physical-device end-to-end tests on minimum and reference iPhones.

## 10.2 G4 acceptance criteria

Onboarding through ten-turn playback completes on both iPhone classes.

Calls, route changes, backgrounding, lock, and memory pressure do not corrupt state or retain recording.

Keychain, backup exclusion, encrypted storage, and deletion inspections pass.

VoiceOver and dynamic-text critical flows pass manual accessibility review.

# 11. Sprint 5: Android integration

## 11.1 Work items

AND-BRIDGE-001: Package arm64-v8a native libraries, implement the generated Flutter plugin, and validate ABI/version mismatch handling.

AND-KEY-001: Implement Android Keystore key wrapping and application-internal protected storage.

AND-AUD-001: Implement AudioRecord, AudioTrack, audio focus, permission timing, route changes, Bluetooth, calls, backgrounding, and cancellation.

AND-MODEL-001: Integrate the approved model-delivery mechanism for private beta and preserve an abstraction for Play Asset Delivery or first-party CDN release.

AND-MEM-001: Implement low-memory and thermal degradation, model eviction, and supported-device capability gating.

AND-UI-001: Complete TalkBack, font scaling, navigation, focus, touch-target, and system-back behavior.

AND-E2E-001: Run physical-device end-to-end tests on minimum and reference Android devices.

## 11.2 G5 acceptance criteria

The complete local workflow passes on both Android classes.

Permission denial, audio focus, interruptions, low memory, and thermal events fail safely.

Keystore, storage, network capture, backup behavior, and deletion inspections pass.

Unsupported devices are rejected before model download with an understandable alternative.

# 12. Sprint 6: cloud experiment, history, and curated search

## 12.1 Experimental cloud adapter

CLOUD-API-001: Implement an OpenAI-compatible adapter using stateless generation, store: false where supported, no remote conversation IDs, structured output, deadline, cancellation, and normalized errors.

CLOUD-ELIG-001: Enforce the provider-eligibility registry before credential validation and every cloud turn. Parent consent or a valid API key SHALL NOT bypass provider/model/region eligibility.

CLOUD-KEY-001: Add parent-only credential entry, direct vault storage, validation, removal, and log/snapshot redaction tests.

CLOUD-MIN-001: Implement a request allowlist containing only policy version, age band, character alias/traits, bounded recent turns, local summary, current transcript, and output constraints.

CLOUD-DISC-001: Add supervised-prototype disclosures explaining external text processing and provider retention. Do not label the experimental adapter suitable for public child use.

CLOUD-POLICY-001: Ship the generic OpenAI-compatible adapter only in development/private-beta channels. OpenAI production use requires an approved under-18 arrangement with the required retention controls; Gemini Developer API remains disabled unless its then-current terms and an approved arrangement satisfy the target child-directed use.

## 12.2 Local history

HIST-001: Implement session-only default, optional encrypted retention, expiry cleanup, parent review, delete session, and delete all.

HIST-SUM-001: Implement bounded local context and local summary generation. Local encrypted history is authoritative; cloud providers receive a separately minimized projection and no remote conversation ID.

## 12.3 Curated search proof of concept

SEARCH-001: Define SearchProvider, source allowlist, SafeSearch requirement, query sanitizer, PII removal, timeout, result cap, and local cache TTL.

SEARCH-FETCH-001: Implement HTTPS-only fetch with private-address blocking, redirect validation, size/type limits, script/style removal, visible-text extraction, and untrusted-evidence labeling.

SEARCH-ANSWER-001: Require grounded responses with source IDs, block unsupported claims where evidence is insufficient, and expose sources in parent mode.

## 12.4 G6 acceptance criteria

Network capture confirms cloud requests contain only allowlisted text fields.

Missing, expired, or incompatible provider eligibility prevents cloud activation and every cloud turn.

Credentials never appear in Dart state, logs, database, URLs, or diagnostics.

Removing a cloud credential leaves local mode functional.

Local history expiry and deletion pass simulated-clock and restart tests.

Search cannot reach loopback/private networks or invoke arbitrary tools.

Retrieved prompt injection text cannot change tool permissions or policy.

# 13. Sprint 7: hardening and private beta

## 13.1 Quality and security

QA-E2E-001: Run the complete matrix on all supported physical devices and desktop systems.

QA-PERF-001: Record cold start, model load, first token, STT/TTS real-time factor, end-to-end latency, peak memory, battery, thermal state, disk use, and 30-turn stability.

QA-PRIV-001: Capture network traffic for onboarding, enrollment, local conversation, cloud conversation, search, deletion, and diagnostics. Verify field allowlists.

QA-SAFE-001: Run the full safety corpus by age band and model/provider. Record unsafe pass rate, over-block rate, malformed output, and fallback quality.

SEC-DSK-001: Test desktop session theft, CSRF, malicious origins, DNS rebinding, WebSocket abuse, oversized payloads, path traversal, and localhost port scanning.

SEC-NATIVE-001: Run dependency, secret, binary-hardening, exported-component, URL-scheme, backup, and filesystem reviews.

A11Y-001: Complete VoiceOver, TalkBack, keyboard, contrast, dynamic text, reduced motion, and child-flow usability reviews.

REL-001: Produce signed/notarized private-beta artifacts, checksums, SBOMs, model/license notices, installation guides, privacy disclosure, test-data instructions, support runbook, and rollback procedure.

## 13.2 G7 acceptance criteria

No open critical or high-severity security/privacy finding.

Safety thresholds approved for supervised beta; known limitations documented.

All mandatory requirements map to passing tests or approved time-bound waivers.

Installation, upgrade, rollback, data migration, uninstall, and delete-all pass.

A supervised pilot can be supported without collecting conversation content.

# 14. Cross-cutting engineering workstreams

## 14.1 Core and API discipline

Version every ABI structure with size and version fields.

Use opaque handles, fixed-width integers, explicit buffer ownership, typed error codes, and explicit free functions.

Never allow std::string, std::vector, Rust layout types, exceptions, or panics to cross an ABI.

Keep all long operations asynchronous and cancellable.

Record ADRs whenever a platform exception changes shared behavior.

## 14.2 Model lifecycle

Maintain signed manifests in source control and release storage.

Pin exact weight hashes and licenses.

Stage and verify downloads before activation.

Preserve one last-known-good version.

Reject engine/model compatibility mismatches.

Keep model files separate from sensitive user encryption domains; integrity, not secrecy, is their primary requirement.

## 14.3 Privacy engineering

Maintain a machine-readable network DTO allowlist.

Add unit tests proving sensitive entities cannot serialize into provider/search requests.

Default to session-only history.

Prevent sensitive data in logs, crash messages, screenshots, filenames, metrics, and diagnostics.

Verify backup behavior and crypto-erasure on each platform.

## 14.4 Safety engineering

Version policies, prompts, filters, and corpus together.

Evaluate every model/policy combination before activation.

Keep deterministic fallbacks independent of model availability.

Do not let parent guidance override immutable safety instructions.

Treat web content and child transcripts as untrusted data.

# 15. Test architecture

| Test layer | Scope | Required in CI |
| --- | --- | --- |
| Unit | Domain rules, policies, state transitions, prompt compilation, retention | Every change |
| Property/fuzz | Parsers, ABI buffers, Unicode names, JSON, URLs, audio metadata | Nightly and release |
| Contract | Provider adapters, schemas, model manifests, desktop API | Every change |
| Integration | SQLCipher, key vaults, inference adapters, migrations, cancellation | Every merge where supported |
| Desktop E2E | Loopback auth and deterministic conversation | Every merge |
| Mobile simulator | Navigation, state, bridge error behavior | Every merge after Sprint 3 |
| Physical device | Audio, inference, interruptions, memory, thermal | Nightly lab/release |
| Safety | Age/model/provider corpus | Every policy/model change |
| Privacy | Network allowlist, storage, backup, deletion, diagnostics | Release and weekly |
| Security | Static analysis, dependencies, desktop/native attack cases | Every release candidate |

## 15.1 Test data rules

Use synthetic text, synthetic/generated audio, or recordings from consenting adult team members. Never put real child conversations, names, voice samples, provider keys, or production endpoints in source, fixtures, CI artifacts, screenshots, or bug reports.

# 16. First sprint-ready backlog

These tickets can be created immediately, before Sprint 0 begins:

| Priority | Ticket | Owner profile | Dependency | Acceptance evidence |
| --- | --- | --- | --- | --- |
| P0 | SPIKE-INF-001 device matrix | Tech lead | None | Approved matrix and measurement script |
| P0 | SPIKE-INF-002 Qwen benchmark | Inference | Device matrix | JSON/CSV benchmark results and recommendation |
| P0 | SPIKE-STT-001 child-speech evaluation | Inference + QA | Test corpus | Accuracy/latency report |
| P0 | SPIKE-TTS-001 voice-cloning evaluation | Inference | Authorized samples | Quality/performance report |
| P0 | SPIKE-ABI-001 cancellable native job | Rust/inference | None | ASan-tested demo |
| P0 | SPIKE-MOB-001 Flutter bridge demo | Mobile | ABI draft | iOS and Android progress/cancel demo |
| P0 | SPIKE-LIC-001 license ledger | Lead/advisor | Candidate list | Approved license table |
| P1 | FOUND-REP-001 monorepo bootstrap | Tech lead | ADR drafts | Reproducible local build |
| P1 | FOUND-CI-001 CI skeleton | QA/lead | Repo | Green build/lint/test workflows |
| P1 | SAFE-CORPUS-001 corpus taxonomy | Safety + QA | Age bands | Versioned initial corpus |

# 17. First ten working days

## Days 1-2

Confirm team roles and decision owners.

Create the repository, issue tracker, ADR template, risk register, and license ledger.

Freeze the initial device matrix and acquire missing test devices.

Define benchmark result schemas and synthetic/authorized test-data rules.

## Days 3-5

Build desktop llama.cpp benchmark harness.

Build STT and TTS command-line benchmark harnesses.

Create the first C ABI job/cancellation prototype.

Draft age-policy schema and safety-corpus categories.

Stand up formatting, lint, unit-test, secret-scan, and dependency-scan CI.

## Days 6-8

Run benchmarks on desktop and mobile reference devices.

Prove Flutter-to-native asynchronous progress and cancellation.

Review memory and thermal results; select initial model candidates.

Record licensing and redistribution findings.

## Days 9-10

Hold G0 review.

Approve or revise minimum devices and model tiers.

Finalize initial ADRs and Sprint 1 backlog.

Publish the benchmark report and revised effort forecast.

# 18. Definition of ready and definition of done

## 18.1 Story ready

A story is ready when it has an owner, user or system outcome, dependencies, interface/schema impact, privacy and safety classification, acceptance tests, representative target devices, and no unresolved product decision that changes its implementation.

## 18.2 Story done

A story is done when code and tests are merged; relevant platforms build; error, cancellation, accessibility, privacy, and logging behavior are handled; schemas and ADRs are updated; no secret or sensitive fixture is introduced; and acceptance evidence is attached.

## 18.3 Release candidate done

A release candidate is done when mandatory requirements are traced, artifacts and models are reproducible and signed, SBOM/license notices exist, migrations and rollback pass, critical device flows pass, safety/privacy/security gates pass, and known limitations are approved and disclosed.

# 19. Decision and escalation ownership

| Decision | Accountable owner | Required reviewers |
| --- | --- | --- |
| Minimum device and model tiers | Technical lead | Inference, mobile, product |
| Model/license approval | Product owner | Technical lead, legal/privacy |
| Age policy and safety thresholds | Product/safety owner | QA, privacy, engineering |
| Cloud provider eligibility | Product owner | Legal/privacy, security, technical lead |
| Storage and retention defaults | Privacy owner | Product, security, mobile |
| ABI/schema compatibility | Technical lead | All platform owners |
| Beta go/no-go | Product owner | Technical lead, QA, safety/privacy |

Block release when a decision affects child safety, provider terms, biometric use, data retention, external transmission, or unsupported-device behavior and has no accountable approval.

# 20. Risks and contingency triggers

| Risk | Trigger | Immediate contingency |
| --- | --- | --- |
| Mobile voice cloning exceeds budget | TTS slower than 1.5x real time or causes termination | Use standard local TTS on affected tier; keep replaceable interface |
| Local 1.7B quality insufficient | Dialogue/safety evaluation misses threshold | Use 4B capable tier; limit local mode; supervised cloud experiment |
| Model combination exceeds memory | Repeated pressure/termination during ten turns | Sequential load/eviction, smaller STT/TTS, lower context, device exclusion |
| Child-speech STT inaccurate | WER above approved threshold | Push-to-talk UX, retry/confirmation, alternate model, narrower device/language scope |
| Desktop browser gateway vulnerable | Any high-severity local attack finding | Suspend desktop beta until fixed and retested |
| Cloud terms unsuitable or eligibility expires | Provider/model/region cannot satisfy child-use and retention requirements | Fail closed; keep adapter development-only; ship local supervised beta |
| Schedule pressure threatens safety/privacy tests | Required corpus/privacy tests incomplete | Reduce platform/features; do not waive mandatory gates |

# 21. Path from private beta to public release

After G7, the public-release program must add:

Qualified legal review for COPPA, biometric/voice laws, regional child-privacy rules, and provider terms.

A production cloud decision: local-only release or a provider/model/region arrangement approved for the target age range and required retention controls, such as an approved zero-data-retention path.

Independent application-security and desktop-gateway review.

Expanded supervised family beta with documented consent and support procedures.

Store privacy/data-safety declarations, parental-gate review, model download rules, and child-category compliance.

Incident response, vulnerability intake, model/policy rollback, support, and deletion runbooks.

Final production device/OS matrix and published minimum storage requirements.

Public release SHALL not inherit the experimental parent-BYOK cloud option without separate approval.

# 22. Immediate start checklist

Name the product owner, technical lead, platform owners, QA owner, and safety/privacy reviewer.

Create the monorepo and issue tracker from the structure in this plan.

Acquire the Sprint 0 device matrix.

Download candidate model weights only from approved sources and record hashes/licenses.

Create synthetic and consenting-adult evaluation data.

Open the ten first-sprint tickets.

Schedule the G0 review for the end of the feasibility sprint.

Begin with benchmark harnesses and the asynchronous ABI prototype, not production UI screens.

# Appendix A: Required ADRs

Shared Rust application core and stable ABI.

Flutter presentation and native host boundaries.

Local LLM runtime and model tiers.

STT and TTS engines and fallback strategy.

Encrypted storage, key management, backup exclusion, and deletion.

Desktop loopback authentication and browser delivery.

Age-policy schema and safety pipeline.

Local history and context minimization.

Experimental cloud adapter boundaries.

Curated web lookup and untrusted-content handling.

Production provider-eligibility registry, approval ownership, expiry, and fail-closed behavior.

# Appendix B: Core engineering commands to define

The repository bootstrap SHALL provide stable commands equivalent to:

make bootstrap       install/check pinned toolchains
make format          format Dart, Rust, C++, Swift/Kotlin glue
make lint            run static analysis
make test            run fast unit and contract tests
make test-safety     run age-policy regression corpus
make test-privacy    run serialization/network allowlist tests
make build-desktop   build signed-development desktop host and UI assets
make build-ios       build iOS simulator/device development artifacts
make build-android   build Android development artifact
make benchmark       run selected inference benchmark suite
make sbom            generate software/model bill of materials

The actual implementation MAY use another task runner, but one documented entry point must orchestrate each workflow consistently in local development and CI.

# Appendix C: Private-beta evidence package

The G7 review package SHALL contain:

Requirements-to-test traceability export.

Device and inference benchmark report.

Safety evaluation report by age band and model/provider.

Privacy network-capture and storage-inspection report.

Security review and resolved findings.

Accessibility checklist and known limitations.

Model/runtime license ledger and SBOM.

Signed artifact checksums and rollback instructions.

Data deletion and retention verification.

Supervised-beta disclosure, consent, and support materials.

# Appendix D: Version 1.1 change summary

Aligns execution with the v5.0 local-first architecture and makes a capability-approved llama.cpp model the MVP completion path.

Adds the signed provider-eligibility registry and separates private-beta BYOK experimentation from production cloud approval.

Makes local encrypted history authoritative and gives external adapters separate minimized DTOs.

Expands curated-search work to enforce sanitized queries, bounded untrusted evidence, and private-network blocking.

Adds provider eligibility and external-mode boundaries to acceptance evidence and release decisions.